## Sheet1
LOG DETAILS - GROUP 3
GROUP 03 - DIGITAL WATCH
BATCH | GROUP NO. | GROUP MEMBERS | ROLL NUMBER | GROUP LEADER | PROJECT TITLE | PROJECT MENTOR | Week No | Date | P/A status (PRESENT/ABSENT) | PROJECT status/WORK done | Target for upcomming week
WEEK 1
B1 | 3 | Mohd Raza | 2 | Mayuri Kadam | Digital Watch | Dr. Sudhakar Mande | 1st week | 11/1/2024 - 12/1/2024 |  | Research on FPGA programming and digital clock design. Project planning, objective definition, resource acquisition. | Research, finalized project objectives, scope, and deliverables
|  | Mayuri Kadam | 16 |  |  | Mr. Ankur G
|  | Aditya Jadhav | 14 |  |  | Miss. Lakshmi Iyer
|  | Himanshu Jogi | 15
WEEK 2
B1 | 3 | Mohd Raza | 2 | Mayuri Kadam | Digital Watch | Dr. Sudhakar Mande | 2nd week | 18/1/2024 - 19/1/2024 |  | Continued research, finalized project objectives, scope, and deliverables. Started setting up the FPGA board and development environment | Complete FPGA board setup, install and configured development tools.
|  | Mayuri Kadam | 16 |  |  | Mr. Ankur G
|  | Aditya Jadhav | 14 |  |  | Miss. Lakshmi Iyer
|  | Himanshu Jogi | 15
WEEK 3
B1 | 3 | Mohd Raza | 2 | Mayuri Kadam | Digital Watch | Dr. Sudhakar Mande | 3rd week | 2024-01-25 |  | Completed FPGA board setup. Installed and configured development tools. Developed a basic understanding of Verilog. | To Start designing architecture and identifying necessary modules.
|  | Mayuri Kadam | 16 |  |  | Mr. Ankur G
|  | Aditya Jadhav | 14 |  |  | Miss. Lakshmi V
|  | Himanshu Jogi | 15
WEEK 4
B1 | 3 | Mohd Raza | 2 | Mayuri Kadam | Digital Watch | Dr. Sudhakar Mande | 4th week | 8/2/2024 - 9/2/2024 |  | Initiated digital clock circuit design. Started designing architecture and identifying necessary modules. | Target was to prepare for Progress Seminar 1.
|  | Mayuri Kadam | 16 |  |  | Mr. Ankur G
|  | Aditya Jadhav | 14 |  |  | Miss. Lakshmi V
|  | Himanshu Jogi | 15
WEEK 5
B1 | 3 | Mohd Raza | 2 | Mayuri Kadam | Digital Watch | Dr. Sudhakar Mande | 5th week | 15/2/2024 - 16/2/2024 |  | Continued digital clock circuit design. Developed modules for clock generation and timekeeping | To Finalized digital clock circuit design and to Implemened and display control modules.
|  | Mayuri Kadam | 16 |  |  | Mr. Ankur G
|  | Aditya Jadhav | 14 |  |  | Miss. Lakshmi V
|  | Himanshu Jogi | 15
WEEK 6
B1 | 3 | Mohd Raza | 2 | Mayuri Kadam | Digital Watch | Dr. Sudhakar Mande | 6th week | 22/2/2024 - 23/2/2024 |  | Finalized digital clock circuit design. Implemented display control modules. Began simulation to verify functionality. | To simulate and validate the design and Troubleshoot any issues encountered.
|  | Mayuri Kadam | 16 |  |  | Mr. Ankur G
|  | Aditya Jadhav | 14 |  |  | Miss. Lakshmi V
|  | Himanshu Jogi | 15
WEEK 7
B1 | 3 | Mohd Raza | 2 | Mayuri Kadam | Digital Watch | Dr. Sudhakar Mande | 7th week | 2024-03-07 |  | Conducted simulation to validate the design. Troubleshooted any issues encountered. Documented the design process. | To Ensure synchronization and accuracy of clock signals.
|  | Mayuri Kadam | 16 |  |  | Mr. Ankur G
|  | Aditya Jadhav | 14 |  |  | Miss. Lakshmi V
|  | Himanshu Jogi | 15
WEEK 8
B1 | 3 | Mohd Raza | 2 | Mayuri Kadam | Digital Watch | Dr. Sudhakar Mande | 8th week | 22/3/2024 - 23/3/2024 |  | Continued simulation and troubleshooting. Ensured synchronization and accuracy of clock signals. | Aim was to prepare for Progress Seminar2.
|  | Mayuri Kadam | 16 |  |  | Mr. Ankur G
|  | Aditya Jadhav | 14 |  |  | Miss. Lakshmi V
|  | Himanshu Jogi | 15
WEEK 9
B1 | 3 | Mohd Raza | 2 | Mayuri Kadam | Digital Watch | Dr. Sudhakar Mande | 9th week | 4/4/2024 - 5/4/2024 |  | Completed simulation phase. Translated Verilog code into FPGA programming language. | Testing and debugging on Xilinx software.
|  | Mayuri Kadam | 16 |  |  | Mr. Ankur G
|  | Aditya Jadhav | 14 |  |  | Miss. Lakshmi V
|  | Himanshu Jogi | 15
WEEK 10
B1 | 3 | Mohd Raza | 2 | Mayuri Kadam | Digital Watch | Dr. Sudhakar Mande | 03th week | 18/4/2024 - 19/4/2024 |  | Initiated FPGA implementation. Programmed the FPGA board with the digital clock design. Conducted initial testing. | To create a ucf file and implement the project on the FPGA board.
|  | Mayuri Kadam | 16 |  |  | Mr. Ankur G
|  | Aditya Jadhav | 14 |  |  | Miss. Lakshmi V
|  | Himanshu Jogi | 15
WEEK 11
B1 | 3 | Mohd Raza | 2 | Mayuri Kadam | Digital Watch | Dr. Sudhakar Mande | 11th week | 25/4/2024 - 26/4/2024 |  | the project on the FPGA board.Continued testing and debugging. Identified and resolved implementation errors or bugs. | To Improve performance and resource utilization and enhance the user interface.
|  | Mayuri Kadam | 16 |  |  | Mr. Ankur G
|  | Aditya Jadhav | 14 |  |  | Miss. Lakshmi V
|  | Himanshu Jogi | 15
WEEK 12
B1 | 3 | Mohd Raza | 2 | Mayuri Kadam | Digital Watch | Dr. Sudhakar Mande | 12th week | 6/5/2024 - 6/5/2024 |  | Reviewed the design for optimization opportunities. Improved performance and resource utilization. Enhanced the user interface. | To implement code on FPGA Board. Conducted final testing to validate functionality and reliability. Prepared documentation and presentation materials. Final Submission
|  | Mayuri Kadam | 16 |  |  | Mr. Ankur G
|  | Aditya Jadhav | 14 |  |  | Miss. Lakshmi V
|  | Himanshu Jogi | 15